## Transaction&Alert Hbase
id | task content | man-hour ( hour/ per person) | comment
1 | configure folder for Hbase reading | 4
2 | Transaction template | 4
3 | import transaction template file to Hbase (given the ssh command) | 8 |  |  | not start
4 | configure project to support hadoop | 8 |  |  | finished
5 | upload file transaction file to linux server | 4 |  |  | need to discuss
6 | java code for triggering import action | 8 |  |  | working
7 | select transaction data with condition | 8 | Hbase not support fuzzy query
8 | delete or soft delete transaction data | 4
9 | update transacton | 4
10 | add single transaction | 4 |  | total: | 84
11 | add single Alert | 8
12 | search Alert with transactions | 8
13 | update Alert | 4 | not mention from functional team
14 | delete or soft delete Alert | 4
15 | select single transaction by id | 4
16
17

## Sceniaro
id | task content | man-hour ( hour/ per person) | comment
1 | add drools to current project | 4
2 | factory function for initial Drools | 4
3 | design db structure for sceniaro part | 8 |  |  | not start
4 | add single rule into seniaro | 8 |  |  | finished
5 | update rule by ID | 8 |  |  | need to discuss
6 | delete rules and single rule | 4 |  |  | working
7 | enable rule or disable rule | 4
8 | get transactions data and run rules engine with defined rule | 20
9 | generate result | 8
10 | insert the result to Alert Hbase table | 8 |  | total: | 76

## Backend
id | task content | man-hour ( hour/ per person) | comment
1 | initial project with spring boot, spring mvc, jpa, hibernate ,mysql,h2 | 8
2 | modulize the structure | 4
3 | design user schema | 4 |  |  | not start
4 | User DAO level create, update, delete, select all , select with condition | 8 |  |  | finished
5 | design user group schema | 4 |  |  | need to discuss
6 | User group DAO level create, update, delete, select all , select with condition | 8 |  |  | working
7 | design role schema | 4
8 | Role DAO level create, update, delete, select all , select with condition | 8
9 | create Login function API, send in (user name, password) | 4
10 | workflow engine API design | 8 |  | total: | 252
11 | create workflow schema, | 4
12 | workflow DAO level create, update, delete, select all , select with condition | 8
13 | generate current workflow | 4
14 | provided workflow api for front end developing | 8
15 | as different user has different menu,design menu structure | 4
16 | Menu DAO level create, update, delete, select all , select with condition | 8
17 | provided menu api , get menu by user id | 8
18 | Transaction Rest API developing | 16
19 | My Alert page API | 16
20 | available Alert page API | 16
21 | Create Alert page API | 16
22 | Close Alert Page API | 16
23 | suppressed Alert page API | 16
24 | upload document for Alert info page | 4
25 | add comment for Alert info page | 16
26 | get account and company information for alert info | 16
27 | close current alert and escalate | 16
28
29

## Frontend
id | task content | man-hour ( hour/ per person) | comment
1 | initial frontend framework with angular js, angular ui router, jquery, bootstrap,normalize | 8
2 | configuration single page application | 4
3 | header and footer reuse developing | 4 |  |  | not start
4 | navagration bar and menu developing | 8 |  |  | finished
5 | page router configuration for alerts module | 8 |  |  | need to discuss
6 | login page | 8 |  |  | working
7 | my alert page | 8
8 | available page | 8
9 | suppressed page | 8
10 | Closed page | 8 |  | total: | 148
11 | alert info page | 16
12 | create alert page | 16
13 | Dashboard page | 20 | unknow time
14 | user manage(role , user goup) | 20
15 | logout , cookie control | 4
16
17
18
19